## GHR_Payroll
RICE Development Tracker
RICE ID | RICE Type | RICE Item | Owned by BAM or Infor | Infor Functional consultant | Overall Status | ANA.050 Analysis Document Status | Developer | Direction | WorkStream | Frequency | Source System | Target System | Complexity | Technology/Tool to Use | Target Completion Date (including Unit Test) | Target Completion for ANA.050 | DES.020 Design Document Status | Target Completion DES.020 | Design Approval status | Target Completion of Approval | Approved By | Development and Unit Test Status | Client Acceptance | Tech Estimate
GHRRICE00001 | Job posts | JoB Boards - Linkedin & Indeed |  | Angelica Marquez | Not Started | Not Started |  | NA | NA | NA | NA | NA
GHRRICE00002 | Payroll tax | Symmetry - Payroll Taxes | Infor | Angelica Marquez | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Symmetry
GHRRICE00003 | I-9 | Tracker Corp - i9 Verification | Infor | Angelica Marquez | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Tracker Corp
GHRRICE00004 |  | Edge - Background Check |  |  | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Edge
GHRRICE00005 |  | WOTC - Work Opportunity Tax Credit |  |  | Not Started | Not Started |  | NA | NA | NA | NA | NA
GHRRICE00006 |  | One-way outgoing SMS texting – to be enabled for TA – IPA configuration – Client should have a subscription to texting service from vendors like Twilio, Telnyx, Vonage etc. |  | Angelica Marquez | Not Started | Not Started |  | NA | NA | NA | NA | NA
GHRRICE00007 |  | MT Payroll to S3 Finance(temporary interface) | Infor | Rolin Pagunsan | Not Started | Not Started |  | NA | NA | NA | NA | NA
GHRRICE00008 |  | Merryl Lynch |  | Dael Manalansan | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Merryl lynch
GHRRICE00009 |  | MHC |  | Rolin Pagunsan | Not Started | Not Started |  | NA | NA | NA | Infor GHR | MHC
GHRRICE00010 |  | Infor GHR to BCBS Interface |  | Dael Manalansan | Not Started | Not Started |  | NA | NA | NA | Infor GHR | BCBS
GHRRICE00011 |  | Infor GHR to Ameritas |  | Dael Manalansan | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Ameritas
GHRRICE00012 |  | Infor GHR to Delta Dental |  | Dael Manalansan | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Delta Dental
GHRRICE00013 |  | Infor GHR to Standard Insurance |  | Dael Manalansan | Not Started | Not Started |  | NA | NA | NA | Infor GHR | Standard Insurance

## Codes (hidden)
Deliverable Status Code | Status | RICE Type
Not Started | Not Started | For Configuration
Started | In Progress | For Development
Deliverable Sent | Testing | For Change Order
Client Reviewing | Completed | Standard, No Setup/Dev Needed
Deliverable Approved | Canceled
On Hold
Review Completed
Client Accepted
N/A